## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Ruchika Sawant
PROJECT NAME: | Student Data Analysis
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-09-04
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Data Analytics |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Harshada Topale
Intern Name | Ruchika Sawant
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
| 2024-08-25 | Incomplete or incorrect data entries in the student dataset. | Data Quality | Yes | Implement more thorough data validation checks before beginning analysis | Conduct an initial audit of the dataset and flag any inconsistencies | Ruchika Sawant | SOLVED
| 2024-08-28 | Encountered issues with inconsistent data formatting, which affected the analysis in Power BI. | Data Preparation | Yes | Ensure consistent data formatting before importing data into Power BI to avoid errors. | Standardized data formatting in Excel before importing into Power BI | Ruchika Sawant | PENDING
| 2024-08-31 | Experienced delays in Power BI report refreshes due to the large size of the Excel file | Performance Optimization | No | Optimize Excel files by reducing unnecessary data and using efficient formulas before linking to Power BI. | Reduced the size of the Excel file and optimized formulas, leading to faster refresh times. | Ruchika Sawant | SOLVED
| 2024-09-03 | Faced challenges in creating specific types of visualizations in Power BI. | Data Visualization | Yes | Explore and practice with more advanced Power BI visualization features or consider using custom visuals. | Spent additional time learning how to use custom visuals and advanced settings in Power BI. | Ruchika Sawant | SOLVED
| 2024-09-08 | Inconsistent data entry in Excel led to errors during Power BI analysis. | Data Quality | Yes | Implement data validation rules in Excel to ensure consistent data entry | Applied data validation and standardized data entry guidelines in Excel. | Ruchika Sawant | SOLVED