## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 5 | 1 | 2 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Student Data Analysis |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 3 | 0 | 0 | 1 | 0 | 0
[10 empty] | Issue | 3 | 0 | 1 | 1 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2024-09-14 | Project Team Lead: | ABC |  |  | Dependency | 3 | 0 | 1 | 0 | 1 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 14 |  |  |  |  | 8
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to do required maintenance on time. | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. | Project Manager | High |  | Open | Risk
2 | Risk | Long supply delivery time | Impact on project schedule | Search for vendors who will deliver the resources on timeand within the proposed budget. | Project Manager | Critical |  | Closed | Assumption
3 | Risk | Incomplete or inaccurate data entries | This could lead to incorrect analysis and misleading insights. | Carefully clean and preprocess the data to fill in gaps and correct errors | IT team | High |  | Open | Issue
4 | Risk | ncorrect assumptions about students' expectations | Could lead to unrealistic recommendations | Cross-reference expectations with market standards | Data Analyst | Moderate |  | Closed | Dependency
5 | Risk | Data privacy concerns : handling sensitive information like email addresses | Breach of privacy could result in legal issues | Ensure data is anonymized and stored securely | Data Analyst | Critical |  | Open
6 | Assumption | All students have provided honest and accurate information | If the information is not accurate, the analysis could be misleading | Validate data wherever possible through cross-referencing with other sources | Data Analyst | Moderate |  | Open | Open
7 | Assumption | The CGPA and expected salary are good indicators of student competence and job expectations. | If these indicators are flawed, the results of the analysis may be invalid | Cross-check assumptions against industry standards and other metrics | Data Analyst | Moderate |  | Closed | Closed
8 | Assumption | The current data reflects the diversity of the student population | If the data is not diverse, the results could be skewed or not applicable to the wider population | Analyze the dataset for diversity and acknowledge limitations in the analysis | Data Analyst | Low |  | Closed
9 | Issue | Some entries in the dataset have missing or incorrect "Family Income" data | Could skew the economic background analysis | Investigate and attempt to correct or estimate missing values | Data Analyst | Moderate |  | Open | Critical
10 | Issue | Duplicate entries in the dataset | Could inflate the analysis results | Identify and remove duplicates | Data Analyst | High |  | Open | High
11 | Issue | Inconsistent or ambiguous survey responses ("How did you come to know about this event?") | Difficult to categorize responses correctly | Reclassify and standardize the responses | Data Analyst | Negligible |  | Closed | Moderate
12 | Dependency | The accuracy and completeness of data from external sources | The quality of your analysis heavily depends on the reliability of the data received | Validate and clean the data before use in analysis | Data Analyst | High |  | Open | Low
13 | Dependency | Availability of software tools for data analysis | Delays or issues with software could hinder progress on the project | Ensure that all required tools are installed and functioning before starting the analysis | Data Analyst | High |  | Closed | Negligible
14 | Dependency | Consistent understanding of data metrics (CGPA, expected salary) | Misinterpretation of these metrics could lead to incorrect analysis results | Establish clear definitions and guidelines for interpreting these metrics | Data Analyst | Low |  | Open
15
16
17
18
19
20
21
22
23
24
25
26